## Sheet1
Bug/ Defect ID | Title | Module/Feature | Short Description | Severity | Priority | Reported By | Date Reported | Steps to Reproduce | Expected Result | Actual Result | Status | Assigned To | Environment | Comments/Attachments | Date Resolved
BG-001 | Newsletter accepts invalid email and Invalid format format | Footer - Newsletter | Newsletter subscription allows invalid emails and email format without validation error. | Medium | High | Anne | 03/10/2025 | 1. Navigate to https://instylekenya.co.ke 2. Scroll to the footer Newsletter section 3. Enter an invalid email format (e.g., 'test123 or sdfegh@gmail.com') 4. Click Subscribe | System should reject invalid emails and show error message. | System accepts invalid email and shows successful subscription email. | New | Jackline | Staging Environment | Occurs on multiple pages consistently. | -
BG-002 | Cart quantity fails to update while inside the cart | Cart | System does not allow cart quantity updates while inside the cart. | Major | High | Anne | 03/10/2025 | 1. Navigate to https://instylekenya.co.ke/cart 2. Add a product to cart 3. Update quantity by clicking addition sign | System should update cart quantity to selected number. | Error with message "Cannot add the quantity to more than8" occurs even if the prouct is one | New | Jackline | Staging environment | Prevents bulk purchases, impacts sales. | -
BG-003 | Wishlist item not removed after adding to cart | Wishlist | Items remain in wishlist even after adding to cart. | Major | Medium | Anne | 03/10/2025 | 1. Navigate to https://instylekenya.co.ke/wishlist 1. Add a product to wishlist 2. Move the product from wishlist to cart 3. Check wishlist again | Product should be removed from wishlist once added to cart. | Product remains in wishlist after being added to cart. | New | Jackline | staging environment | Causes duplication in cart and wishlist.. | -
BG-004 | Password reset email not sent | Authentication | Users do not receive password reset link via email. | Critical | High | Anne | 03/10/2025 | 1. Go to login page https://instylekenya.co.ke/account 2. Click 'Forgot password' 3. Enter registered email 4. Check email inbox | User should receive password reset email with link. | No email received even after multiple attempts. | New | Jackline | Staging Environment | Blocks account recovery | -
BG-005 | Sorting by Price (Low to High) not functioning | Product Catalogue | Products not sorted from lowest to highest price. | Medium | Medium | Anne | 2025-10-03 | 1. Navigate to https://instylekenya.co.ke/shop 2. Select sorting option 'Price: Low to High' 3. Observe product arrangement | Products should be displayed from lowest to highest price. | Products remain unsorted and the sorting option is not clickable | New | Jackline- | Staging Environment | Affects product discovery for users. | -
BG-006 | Sorting by Price (High to Low) not functioning | Product Catalogue | Products not sorted from highest to lowest price. | Medium | Medium | Anne | 2025-10-03 | 1.Navigate to https://instylekenya.co.ke/shop 2.Select sorting option “Price: High to Low” 3.Observe product arrangement | Products should be displayed from highest to lowest price. | Products remain unsorted and the sorting option is not clickable | New | Jackline | Staging Environment | Affects product discovery for users.
BG-007 | Sorting by Latest not functioning | Product Catalogue | “Sort by Latest” does not display newly added products first. | Medium | Medium | Anne | 2025-10-03 | 1.Navigate to https://instylekenya.co.ke/shop 2.Select sorting option “Latest” 3.Observe product arrangement | Newest products should appear at the top of the list. | Products appear in random randomly and the sorting option is not clickable | New | Jackline | Staging environment | Prevents customers from finding new arrivals easily.
BG-008 | Sorting by Average Rating not functioning | Product Catalogue | “Sort by Average Rating” does not rank products according to customer ratings. | Medium | Medium | Anne | 2025-10-03 | 1.Navigate to https://instylekenya.co.ke/shop 2.Select sorting option “Average Rating” 3Observe product arrangement | Products should be ordered from highest-rated to lowest-rated. | Products remain unsorted or incorrectly ordered. | New | Jackline | Staging environment | Reduces credibility of ratings system.